## Task Tracker
IB Health — Medical Term Simplifier · Project Tracker ¦ Owner: Preetha ¦ 23 Jun – 22 Jul 2025
Task ID | Phase | Task Name | Description | Deliverable | Priority | Start Date | End Date | Status | % Done | Dependencies | Remarks
F1-00 | Feature 1 | Literature Survey & Model Evaluation | Review biomedical NLP literature; evaluate BioClinical ModernBERT, OpenMedFocus, IBM Granite Healthcare | Model comparison report + selected stack | Critical | 23 Jun 2025 | 26 Jun 2025 | Completed | 100% | — | Done 19–22 Jun. Discussed architecture with Ben on 22 Jun.
F1-01 | Feature 1 | Dataset Collection & Preparation | Collect clinical reports (discharge summaries, EHRs, lab results); annotate & split train/val/test | Curated & annotated clinical dataset | Critical | 23 Jun 2025 | 29 Jun 2025 | In Progress | 30% | F1-00 | Target ≥500 de-identified reports across specialties.
F1-02 | Feature 1 | BioClinical ModernBERT — Fine-tuning Setup | Configure training pipeline; set up GPU environment; define NER label schema | Fine-tuning pipeline + config files | Critical | 24 Jun 2025 | 29 Jun 2025 | In Progress | 20% | F1-00 | Label schema: Disease, Symptom, Medication, Procedure, Test, Value.
F1-03 | Feature 1 | Clinical Entity Extraction (NER) | Fine-tune BioClinical ModernBERT on dataset; extract diseases, symptoms, meds, procedures, test results | NER model + structured JSON output per report | Critical | 27 Jun 2025 | 03 Jul 2025 | To Do | 0% | F1-01,F1-02 | Output: structured JSON with entities + confidence scores.
F2-01 | Feature 2 | Accent Adaptation Model — Familiarization & Setup | Study selected model architecture, deployment requirements, hardware specs | Setup guide + deployment requirements doc | High | 23 Jun 2025 | 27 Jun 2025 | In Progress | 40% | — | Model already selected; no research needed.
F2-02 | Feature 2 | Environment Configuration | Configure dev/test environment: Docker, CUDA, model weights, dependencies | Configured & tested environment | High | 25 Jun 2025 | 28 Jun 2025 | In Progress | 60% | F2-01 | Ensure GPU availability for inference benchmarking.
F1-04 | Feature 1 | Medical Concept Understanding Layer | Pass NER output through OpenMedFocus to capture clinical context, relationships, severity | Context extraction module (Python) | Critical | 30 Jun 2025 | 05 Jul 2025 | To Do | 0% | F1-03 | Maps entity graph → clinical intent. Key for accurate simplification.
F1-05 | Feature 1 | Educational-Level Mapping Design | Design prompting strategy + output schemas for Beginner, Intermediate, Advanced levels | Level-mapping spec doc + prompt templates | High | 30 Jun 2025 | 03 Jul 2025 | To Do | 0% | F1-04 | Beginner: grade 6–8 reading; Intermediate: undergrad health; Advanced: clinical.
F2-03 | Feature 2 | Baseline Model Testing & Benchmarking | Run baseline inference on accent adaptation model; measure WER, MOS, RTF, memory | Baseline benchmark report | High | 28 Jun 2025 | 03 Jul 2025 | To Do | 0% | F2-02 | Target: RTF < 0.2, MOS ≥ 3.5.
F2-04 | Feature 2 | Speech Sample Preparation | Collect & label speech samples across Indian accents; explore Project Vaani (109+ dialects) | Labelled speech evaluation dataset | High | 28 Jun 2025 | 04 Jul 2025 | To Do | 0% | F2-01 | Min 50 speakers; include Tamil, Hindi, Telugu, Kannada, Bengali.
MS-01 | Milestone | ⭐ Milestone 1 — NLP Core + Speech Baseline Ready | NER pipeline functional; accent model baseline benchmarked | Demo: entity extraction on 3 sample reports | Critical | 05 Jul 2025 | 05 Jul 2025 | To Do | 0% | F1-04,F2-03 | Internal review checkpoint. Share with Ben.
F1-06 | Feature 1 | Simplification Engine — IBM Granite Healthcare Integration | Integrate IBM Granite Healthcare as simplification LLM; implement 3-level explanation generation | Simplification engine (API + prompt layer) | Critical | 06 Jul 2025 | 11 Jul 2025 | To Do | 0% | F1-04,F1-05 | Pipeline: Structured JSON → Granite → Beginner/Intermediate/Advanced text.
F1-07 | Feature 1 | Report Upload Interface & API | Build REST API for clinical report ingestion (PDF, text); connect to NLP pipeline | FastAPI backend + upload endpoint | High | 06 Jul 2025 | 10 Jul 2025 | To Do | 0% | F1-03 | Accept PDF & plain text. Return structured + simplified output as JSON.
F2-05 | Feature 2 | Accent Preservation & Quality Testing | Test accent-aware output across regional Indian accents; perceptual A/B evaluation | Accent quality test report | High | 05 Jul 2025 | 10 Jul 2025 | To Do | 0% | F2-03,F2-04 | Side-by-side listener evaluation for at least 3 accent groups.
F2-06 | Feature 2 | Project Vaani — Dialect Capability Evaluation | Evaluate dialect-specific features from Project Vaani dataset; identify supported dialects | Dialect coverage report | Medium | 05 Jul 2025 | 10 Jul 2025 | To Do | 0% | F2-04 | 109+ dialects; identify top 10 for initial support.
F3-01 | Future Layer | IndicTrans2 Integration — Setup & Translation Pipeline | Integrate IndicTrans2 for English → Indian language translation of medical explanations | Translation pipeline (EN → 5 Indian languages) | High | 07 Jul 2025 | 12 Jul 2025 | To Do | 0% | F1-06 | Initial languages: Tamil, Hindi, Telugu, Kannada, Bengali.
MS-02 | Milestone | ⭐ Milestone 2 — Simplification Engine Live | End-to-end: upload report → entity extraction → Granite simplification → 3-level output | Live demo of full Feature 1 pipeline | Critical | 12 Jul 2025 | 12 Jul 2025 | To Do | 0% | F1-06,F1-07 | Share demo recording with Ben + team.
F1-08 | Feature 1 | Evaluation & Validation — Simplification Quality | Evaluate outputs: BLEU, ROUGE-L, Flesch-Kincaid readability; clinician spot-check | Evaluation report with metrics table | Critical | 13 Jul 2025 | 17 Jul 2025 | To Do | 0% | F1-06 | Target: FK grade ≤ 8 for Beginner; accuracy ≥ 85% clinician approval.
F2-07 | Feature 2 | Performance Benchmarking & Scalability Audit | Measure inference speed, GPU/CPU memory, throughput; test concurrent request handling | Scalability & performance report | High | 13 Jul 2025 | 16 Jul 2025 | To Do | 0% | F2-05 | Target: < 200 ms per inference; ≤ 4 GB VRAM.
F2-08 | Feature 2 | Integration — Accent Adaptation + Medical Term Simplifier | Connect TTS with accent model to simplified text output; build unified response payload | Integrated text-to-speech module | Critical | 13 Jul 2025 | 17 Jul 2025 | To Do | 0% | F1-06,F2-05 | Simplified text → Accent-adapted TTS → Audio response.
F3-02 | Future Layer | Regional Language TTS + Dialect-Aware Speech | Pipe IndicTrans2 output into dialect-aware TTS; evaluate accent-aware localized speech | Localized speech output (3+ languages) | Medium | 14 Jul 2025 | 19 Jul 2025 | To Do | 0% | F3-01,F2-08 | Initial: Tamil + Hindi. Accent-aware TTS using Project Vaani dialect layer.
F1-09 | Feature 1 | Multilingual Expansion Planning | Document integration points for IndicTrans2 in Feature 1 pipeline; stub API hooks | Multilingual pipeline spec doc | Medium | 15 Jul 2025 | 18 Jul 2025 | To Do | 0% | F3-01,F1-06 | Ensures smooth handoff to Future Layer post-deployment.
F1-10 | Feature 1 | End-to-End Integration & System Testing | Full pipeline test: report upload → NER → concept understanding → simplification → speech output | E2E test report + bug log | Critical | 19 Jul 2025 | 21 Jul 2025 | To Do | 0% | F1-08,F2-08 | Test 20 sample reports across specialties.
F2-09 | Feature 2 | End-to-End Validation — Accent + Simplification | Validate accent-adapted speech output quality when paired with simplified medical text | Validation report + audio samples | Critical | 19 Jul 2025 | 21 Jul 2025 | To Do | 0% | F2-08,F1-10 | Perceptual quality check by 3 evaluators.
F1-11 | Feature 1 | Deployment Packaging — Docker + API Docs | Containerise full pipeline; write API documentation; prepare deployment manifest | Docker image + API docs + deployment guide | Critical | 20 Jul 2025 | 22 Jul 2025 | To Do | 0% | F1-10 | Target: single docker-compose up command to run full system.
MS-03 | Milestone | ⭐ MILESTONE 3 — Product Ready for Deployment | All features integrated, tested, and containerised. Deployment-ready handoff. | Deployable build + full documentation | Critical | 22 Jul 2025 | 22 Jul 2025 | To Do | 0% | F1-11,F2-09,F3-02 | 22 Jul 2025 — Final delivery. Present to Ben.

## Milestone Tracker
IB Health — Milestone Tracker ¦ Target: Deployable Product by 22 Jul 2025
Milestone ID | Milestone | Target Date | Feature(s) | Dependencies | Status | Success Criteria
MS-00 | Literature Survey & Architecture Finalized | 22 Jun 2025 | F1 | — | Completed | Model stack confirmed; pipeline design approved by Ben
MS-01 | NLP Core + Speech Baseline Ready | 05 Jul 2025 | F1, F2 | F1-04, F2-03 | To Do | NER demo on 3 reports; accent baseline MOS ≥ 3.5
MS-02 | Simplification Engine Live | 12 Jul 2025 | F1 | F1-06, F1-07 | To Do | Upload → extract → simplify → 3-level output demo
MS-03 | 🚀 Product Ready for Deployment | 22 Jul 2025 | F1, F2, F3 | F1-11, F2-09, F3-02 | To Do | Docker build runs; API docs complete; E2E tests pass

## Progress Dashboard
IB Health — Medical Term Simplifier · Progress Dashboard
Feature | Description | Total Tasks | Completed | In Progress | To Do | Avg % Done | Critical Tasks
Feature 1 | Medical Report Simplification | 12 | 1 | 2 | 9 | 12% | 9
Feature 2 | Accent Adaptation & Speech | 9 | 0 | 2 | 7 | 11% | 2
Future Layer | Multilingual & Dialect | 2 | 0 | 0 | 2 | 0% | 0
ALL FEATURES | Combined | 23 | 1 | 4 | 18 | 10% | 11
Timeline ¦ Week 1: 23–29 Jun ¦ Week 2: 30 Jun–6 Jul ¦ Week 3: 7–13 Jul ¦ Week 4: 14–20 Jul ¦ Final Sprint: 21–22 Jul ¦ Deadline: 22 Jul 2025
Status Key
Completed | In Progress | To Do
Critical | High | Medium

## Pipeline Reference
IB Health — Pipeline Reference
Feature 1 — Medical Report Simplification
Pipeline Flow | Clinical Report → BioClinical ModernBERT (NER) → OpenMedFocus (Context) → Structured Clinical JSON → IBM Granite Healthcare → Beginner / Intermediate / Advanced Explanation
Feature 2 — Accent Adaptation & Speech
Pipeline Flow | User Speech → Accent Adaptation Model → Accent-Aware Representation → TTS Generation → Personalized Speech Output
Future Layer — Multilingual & Dialect
Pipeline Flow | English Medical Explanation → IndicTrans2 Translation → Regional Language Output → Dialect Layer (Project Vaani) → Accent-Aware TTS → Localized Speech Output
Integrated End-to-End Pipeline
Pipeline Flow | Clinical Report Upload → NER (BioClinical ModernBERT) → Context (OpenMedFocus) → Simplification (IBM Granite) → Simplified Text → IndicTrans2 → Accent TTS → Localized Personalized Audio